## Calendar
| January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July
| Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tues | Wed | Thu | Fri | Sat | Sun | Mon | Tues | Wed | Thu | Fri | Sat | Sun | Mon | Tues | Wed | Thu | Fri | Sat | Sun | Mon | Tues | Wed | Thu | Fri | Sat | Sun | Mon | Tues | Wed | Thu | Fri | Sat | Sun | Mon | Tues | Wed | Thu | Fri
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
PI Planning Event: 1/3-1/6 | January Tue: PI Planning Event
Sprint 28: 1/9-1/13 | January Mon: Sprint 50
Sprint 29: 1/16-1/27 | January Mon: Sprint 51
Sprint 30: 1/30-2/10 | January Mon: Sprint 52
Sprint 31: 2/13-2/24 | February Mon: Sprint 53
Sprint 32: 2/27-3/10 | February Mon: Sprint 54
Sprint 33: 3/13-3/24 | March Mon: Sprint 55
UAT ([Team Letter][Sprint#] UAT) | January Tue: D27 UAT; January Mon: D28 UAT; January Mon: D29 UAT; February Mon: D30 UAT; February Mon: D31 UAT; March Mon: D32 UAT; March Mon: D33 UAT
Releases ([Team Letter][Sprint#]R) | January Thu: D27R; January Wed: D28R; February Wed: D29R; February Wed: D30R; March Wed: D31R; March Wed: D32R; March Wed: D33R
Dev Day (DD) / No Meeting Day (NMD) | January Thu: DD; January Thu: NMD; February Thu: DD; February Thu: NMD; March Thu: DD; March Thu: NMD; April Thu: DD; April Thu: NMD; May Thu: DD; May Thu: NMD; June Thu: DD; June Thu: NMD
Holiday (H) | January Mon: H; May Mon: H-US; July Tues: H-US
PI Day Number | [8 empty] | 1 | 2 | 3 | 4 | 5 |  |  | 6 | 7 | 8 | 9 | 10 |  |  | 11 | 12 | 13 | 14 | 15 |  |  | 16 | 17 | 18 | 19 | 20 |  |  | 21 | 22 | 23 | 24 | 25 |  |  | 26 | 27 | 28 | 29 | 30 |  |  | 31 | 32 | 33 | 34 | 35 |  |  | 36 | 37 | 38 | 39 | 40 |  |  | 41 | 42 | 43 | 44 | 45 |  |  | 46 | 47 | 48 | 49 | 50 |  |  | 51 | 52 | 53 | 54 | 55 | [9 empty] | 1 | 2 | 3 | 4 | 5 |  |  | 6 | 7 | 8 | 9 | 10 |  |  | 11 | 12 | 13 | 14 | 15 |  |  | 16 | 17 | 18 | 19 | 20 |  |  | 21 | 22 | 23 | 24 | 25 |  |  | 26 | 27 | 28 | 29 | 30 |  |  | 31 | 32 | 33 | 34 | 35 |  |  | 36 | 37 | 38 | 39 | 40 |  |  | 41 | 42 | 43 | 44 | 45 |  |  | 46 | 47 | 48 | 49 | 50 |  |  | 51 | 52 | 53 | 54 | 55 |  |  | 56 | 57 | 58 | 59 | 60 |  |  | 61 | 62 | 63 | 64 | 65
Percent Complete | [8 empty] | 1.818% | 3.636% | 5.455% | 7.273% | 9.091% |  |  | 10.91% | 12.73% | 14.55% | 16.36% | 18.18% |  |  | 20% | 21.82% | 23.64% | 25.45% | 27.27% |  |  | 29.09% | 30.91% | 32.73% | 34.55% | 36.36% |  |  | 38.18% | 40% | 41.82% | 43.64% | 45.45% |  |  | 47.27% | 49.09% | 50.91% | 52.73% | 54.55% |  |  | 56.36% | 58.18% | 60% | 61.82% | 63.64% |  |  | 65.45% | 67.27% | 69.09% | 70.91% | 72.73% |  |  | 74.55% | 76.36% | 78.18% | 80% | 81.82% |  |  | 83.64% | 85.45% | 87.27% | 89.09% | 90.91% |  |  | 92.73% | 94.55% | 96.36% | 98.18% | 100% | [9 empty] | 1.538% | 3.077% | 4.615% | 6.154% | 7.692% |  |  | 9.231% | 10.77% | 12.31% | 13.85% | 15.38% |  |  | 16.92% | 18.46% | 20% | 21.54% | 23.08% |  |  | 24.62% | 26.15% | 27.69% | 29.23% | 30.77% |  |  | 32.31% | 33.85% | 35.38% | 36.92% | 38.46% |  |  | 40% | 41.54% | 43.08% | 44.62% | 46.15% |  |  | 47.69% | 49.23% | 50.77% | 52.31% | 53.85% |  |  | 55.38% | 56.92% | 58.46% | 60% | 61.54% |  |  | 63.08% | 64.62% | 66.15% | 67.69% | 69.23% |  |  | 70.77% | 72.31% | 73.85% | 75.38% | 76.92% |  |  | 78.46% | 80% | 81.54% | 83.08% | 84.62% |  |  | 86.15% | 87.69% | 89.23% | 90.77% | 92.31% |  |  | 93.85% | 95.38% | 96.92% | 98.46% | 100%
Other Events | January Thu: Development Day; January Thu: No-meeting Day; February Thu: Development Day; April Thu: Development Day; April Thu: No-meeting Day; May Thu: Development Day; May Thu: No-meeting Day; June Thu: Development Day; June Thu: No-meeting Day
[47 empty] | No-meeting Day | [13 empty] | Development Day
No-meeting Day

## Team Meetings and Activites
Planned Meetings & Activities | Sprint Duration - 2 Weeks (10 Working Days) | [9 empty] | Team Meeting Minutes | Training, Prof Dev, QA, & Support Minutes | Total Hours | Recommended Feature or Epic | Recommended Worklog Activity for Time Tracking | Notes
Scrum Ceremonies | M | Tu | W | Th | F | M | Tu | W | Th | F
Sprint Planning | Sprint Duration - 2 Weeks (10 Working Days) F: 60 | 60 |  | 1 | General Work | Project Planning
Daily Update/Scrum Call | Sprint Duration - 2 Weeks (10 Working Days) Tu: 30; Sprint Duration - 2 Weeks (10 Working Days) Th: 60; Sprint Duration - 2 Weeks (10 Working Days) Tu: 30; Sprint Duration - 2 Weeks (10 Working Days) Th: 60 | 180 |  | 3 | General Work | Project Planning
Grooming | Sprint Duration - 2 Weeks (10 Working Days) M: 30; Sprint Duration - 2 Weeks (10 Working Days) Th: 60; Sprint Duration - 2 Weeks (10 Working Days) M: 30; Sprint Duration - 2 Weeks (10 Working Days) Th: 60 | 180 |  | 3 | General Work | Project Planning
Sprint Review, Planning, & Retrospective | Sprint Duration - 2 Weeks (10 Working Days) F: 60 | 60 |  | 1 | General Work | Project Planning
Sprint Demo | Sprint Duration - 2 Weeks (10 Working Days) M: 30 | 30 |  | 0.5 | General Work | Project Planning
QA Weekly Check-in | Sprint Duration - 2 Weeks (10 Working Days) W: 30; Sprint Duration - 2 Weeks (10 Working Days) W: 30 | 60 |  | 1 | General Work | QA - Testing
Training, Prof Development, QA, Support Activities - (minimum/average high-level guess in minutes; this will differ by team member) | M | Tu | W | Th | F | M | Tu | W | Th | F
Manager/Employee 1-1s | M: 30 |  | 30 | 0.5 | Not Logged | N/A
Training/Self Development | 30 Th: 180 |  | 180 | 3 | Not Logged | N/A
Support | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 |  | 1200 | 20 | Specific Bugs | Support | Estimated Average Support (for all Team Members)
QA | [13 empty] | Specific Stories | QA - Testing
Tech Swarm Sessions | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  | 300 | 5 | Specific Stories or General Work | Requirements / Business Process
Total Time | [10 empty] | 570 | 1710 | 38
Total Time as Percentage of Sprint | [10 empty] | 11.88% | 35.62% | 47.5%

## 1. Business Objectives
Business Objectives |  |  | Total Story Points per PI |  |  | 150 |  |  | Supporting Features
Enter business objectives below. These are not necessarily features, but are generally overarching. | [8 empty] | These are the features that will support/achieve the objectives to the left.
↕ | Business Objectives/Features | Priority | Impact/Value | Size (Effort) | Est Pts | Real Pts | % of PI | PI | Feature(s) | Planned? | Feature Link | Feature Stories | Parent/Main | Dependency 1 | Dependency 2 | Dependency 3
1 | Feature A | High | Medium | M | 20 | 23 | 13.33% | Q1
2 | Feature B | Medium | High | M | 20 | 20 | 13.33% | Q2
3 | Feature C | Medium | High | XL | 40 | 40 | 26.67% | Q3
4 | Feature D | Low | Low | M | 21 | 21 | 14% | Q4
5 | Feature E | Low | Medium | S | 10 | 10 | 6.667% | QX
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
Q | Points per Quarter
Q1 | 23
Q2 | 20
Q3 | 40
Q4 | 21
QX | 10

## 2. PI Feature Backlog
Program Increment Feature Backlog
List of features included in the Program Increment
↕ | Feature Key | Link | Stories | Committed? | Feature Summary | Feature Key 2 | Deep Dive # | Notes | Feature Color Key | Name
1 | ITAPPS-00000 | Link | Stories | Committed | Feature A |  | 1 |  | Feature | Light Gray
[9 empty] | Feature | Red
[9 empty] | Feature | Orange
[9 empty] | Feature | Yellow
[9 empty] | Feature | Green
[9 empty] | Feature | Teal
[9 empty] | Feature | Blue
[9 empty] | Feature | Periwinkle
[9 empty] | Feature | Violet
[9 empty] | Feature | Indigo
[9 empty] | Feature | Dark Gray
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use Format Painter to Copy Color to Feature Summary

## 3. PI Issue Backlog
PI Issue Backlog
List of stories (broken down from features) included in the Program Increment
↕ | Source | Issue Key | Story/Bug Summary | Story Link | Priority | Points | Feature Key | Feat. Link | Feature Summary | Notes | Feature Color Key | Name
3 | [10 empty] | Feature | Light Gray
4 | [10 empty] | Feature | Red
5 | [10 empty] | Feature | Orange
6 | [10 empty] | Feature | Yellow
7 | [10 empty] | Feature | Green
8 | [10 empty] | Feature | Teal
9 | [10 empty] | Feature | Blue
10 | [10 empty] | Feature | Periwinkle
11 | [10 empty] | Feature | Violet
12 | [10 empty] | Feature | Indigo
13 | [10 empty] | Feature | Dark Gray
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
Note on N5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use Format Painter to Copy Color to Feature Summary

## CP S50
Capacity Planning | Sprint 50
|  |  |  | OPTION 1: | [10 empty] | OPTION 2:
|  |  |  | Allocate hours; enter availability per day | [10 empty] | Override Availability
Name | Title | Estimated % of Time Dedicated to this Team | Estimated Dedicated Hours (Calculated) | M 01 | Tu 02 | W 03 | Th 04 | F 05 | M 06 | Tu 07 | W 08 | Th 09 | F 10 | Hours Available (Calculated by Day Availability) | Time Off (Override) | Max Possible Capacity (Calculated) | % Time for Training, QA, and Support | Estimated Hours Dedicated to Team Meetings | Available Hours (Calculated) | Estimation = hours/8 (Calculated) | Planned Story Points | Notes and Comments
PA 1 | Product Analyst | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 30% | 12% | 46.4 | 5.8 | 5
PA 2 | Product Analyst | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 80% | 12% | 6.4 | 0.8 | 2
SE 1 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 2 | Software Engineer | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 3 | Software Engineer | 85% | 68 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 4 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 6
QA 1 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 50% | 12% | 30.4 | 3.8 | 4
QA 2 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 5
|  |  | 596 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 640 | 0 | 640 | 33.75% | 12% | 347.2 | 43.4 | 40
|  |  | July | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
Totals |  |  | Capacity
Total Hours Before Time Off |  |  | 596
Max Possible Hours After Time Off |  |  | 640
Hours Available after Training, QA, Support, and Meetings |  |  | 347.2
Estimated Capacity (in approx. Story Points) |  |  | 43.4
Final Agreed Upon Team Capacity (in Story Points) |  |  | 40
Buffer/Adjustments
Total Sprint Capacity |  |  | 40
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Decrease percentage to account for time required for work on other teams.
Note on S6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Required HR Training, Professional Development Days, QA and Release, Support work.
Note on T6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-1s, Stand-up, Grooming, Sprint Review, Sprint Retro, Sprint Planning, Town Halls, etc.

## CP S51
Capacity Planning | Sprint 51
|  |  |  | OPTION 1: | [10 empty] | OPTION 2:
|  |  |  | Allocate hours; enter availability per day | [10 empty] | Override Availability
Name | Title | Estimated % of Time Dedicated to this Team | Estimated Dedicated Hours (Calculated) | M 01 | Tu 02 | W 03 | Th 04 | F 05 | M 06 | Tu 07 | W 08 | Th 09 | F 10 | Hours Available (Calculated by Day Availability) | Time Off (Override) | Max Possible Capacity (Calculated) | % Time for Training, QA, and Support | Estimated Hours Dedicated to Team Meetings | Available Hours (Calculated) | Estimation = hours/8 (Calculated) | Planned Story Points | Notes and Comments
PA 1 | Product Analyst | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 30% | 12% | 46.4 | 5.8 | 5
PA 2 | Product Analyst | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 80% | 12% | 6.4 | 0.8 | 2
SE 1 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 2 | Software Engineer | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 3 | Software Engineer | 85% | 68 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 4 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 6
QA 1 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 50% | 12% | 30.4 | 3.8 | 4
QA 2 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 5
|  |  | 596 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 640 | 0 | 640 | 33.75% | 12% | 347.2 | 43.4 | 40
|  |  | July | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
Totals |  |  | Capacity
Total Hours Before Time Off |  |  | 596
Max Possible Hours After Time Off |  |  | 640
Hours Available after Training, QA, Support, and Meetings |  |  | 347.2
Estimated Capacity (in approx. Story Points) |  |  | 43.4
Final Agreed Upon Team Capacity (in Story Points) |  |  | 40
Buffer/Adjustments
Total Sprint Capacity |  |  | 40
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Decrease percentage to account for time required for work on other teams.
Note on S6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Required HR Training, Professional Development Days, QA and Release, Support work.
Note on T6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-1s, Stand-up, Grooming, Sprint Review, Sprint Retro, Sprint Planning, Town Halls, etc.

## CP S52
Capacity Planning | Sprint 52
|  |  |  | OPTION 1: | [10 empty] | OPTION 2:
|  |  |  | Allocate hours; enter availability per day | [10 empty] | Override Availability
Name | Title | Estimated % of Time Dedicated to this Team | Estimated Dedicated Hours (Calculated) | M 01 | Tu 02 | W 03 | Th 04 | F 05 | M 06 | Tu 07 | W 08 | Th 09 | F 10 | Hours Available (Calculated by Day Availability) | Time Off (Override) | Max Possible Capacity (Calculated) | % Time for Training, QA, and Support | Estimated Hours Dedicated to Team Meetings | Available Hours (Calculated) | Estimation = hours/8 (Calculated) | Planned Story Points | Notes and Comments
PA 1 | Product Analyst | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 30% | 12% | 46.4 | 5.8 | 5
PA 2 | Product Analyst | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 80% | 12% | 6.4 | 0.8 | 2
SE 1 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 2 | Software Engineer | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 3 | Software Engineer | 85% | 68 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 4 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 6
QA 1 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 50% | 12% | 30.4 | 3.8 | 4
QA 2 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 5
|  |  | 596 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 640 | 0 | 640 | 33.75% | 12% | 347.2 | 43.4 | 40
|  |  | July | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
Totals |  |  | Capacity
Total Hours Before Time Off |  |  | 596
Max Possible Hours After Time Off |  |  | 640
Hours Available after Training, QA, Support, and Meetings |  |  | 347.2
Estimated Capacity (in approx. Story Points) |  |  | 43.4
Final Agreed Upon Team Capacity (in Story Points) |  |  | 40
Buffer/Adjustments
Total Sprint Capacity |  |  | 40
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Decrease percentage to account for time required for work on other teams.
Note on S6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Required HR Training, Professional Development Days, QA and Release, Support work.
Note on T6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-1s, Stand-up, Grooming, Sprint Review, Sprint Retro, Sprint Planning, Town Halls, etc.

## CP S53
Capacity Planning | Sprint 53
|  |  |  | OPTION 1: | [10 empty] | OPTION 2:
|  |  |  | Allocate hours; enter availability per day | [10 empty] | Override Availability
Name | Title | Estimated % of Time Dedicated to this Team | Estimated Dedicated Hours (Calculated) | M 01 | Tu 02 | W 03 | Th 04 | F 05 | M 06 | Tu 07 | W 08 | Th 09 | F 10 | Hours Available (Calculated by Day Availability) | Time Off (Override) | Max Possible Capacity (Calculated) | % Time for Training, QA, and Support | Estimated Hours Dedicated to Team Meetings | Available Hours (Calculated) | Estimation = hours/8 (Calculated) | Planned Story Points | Notes and Comments
PA 1 | Product Analyst | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 30% | 12% | 46.4 | 5.8 | 5
PA 2 | Product Analyst | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 80% | 12% | 6.4 | 0.8 | 2
SE 1 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 2 | Software Engineer | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 3 | Software Engineer | 85% | 68 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 4 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 6
QA 1 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 50% | 12% | 30.4 | 3.8 | 4
QA 2 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 5
|  |  | 596 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 640 | 0 | 640 | 33.75% | 12% | 347.2 | 43.4 | 40
|  |  | July | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
Totals |  |  | Capacity
Total Hours Before Time Off |  |  | 596
Max Possible Hours After Time Off |  |  | 640
Hours Available after Training, QA, Support, and Meetings |  |  | 347.2
Estimated Capacity (in approx. Story Points) |  |  | 43.4
Final Agreed Upon Team Capacity (in Story Points) |  |  | 40
Buffer/Adjustments
Total Sprint Capacity |  |  | 40
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Decrease percentage to account for time required for work on other teams.
Note on S6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Required HR Training, Professional Development Days, QA and Release, Support work.
Note on T6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-1s, Stand-up, Grooming, Sprint Review, Sprint Retro, Sprint Planning, Town Halls, etc.

## CP S54
Capacity Planning | Sprint 54
|  |  |  | OPTION 1: | [10 empty] | OPTION 2:
|  |  |  | Allocate hours; enter availability per day | [10 empty] | Override Availability
Name | Title | Estimated % of Time Dedicated to this Team | Estimated Dedicated Hours (Calculated) | M 01 | Tu 02 | W 03 | Th 04 | F 05 | M 06 | Tu 07 | W 08 | Th 09 | F 10 | Hours Available (Calculated by Day Availability) | Time Off (Override) | Max Possible Capacity (Calculated) | % Time for Training, QA, and Support | Estimated Hours Dedicated to Team Meetings | Available Hours (Calculated) | Estimation = hours/8 (Calculated) | Planned Story Points | Notes and Comments
PA 1 | Product Analyst | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 30% | 12% | 46.4 | 5.8 | 5
PA 2 | Product Analyst | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 80% | 12% | 6.4 | 0.8 | 2
SE 1 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 2 | Software Engineer | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 3 | Software Engineer | 85% | 68 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 4 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 6
QA 1 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 50% | 12% | 30.4 | 3.8 | 4
QA 2 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 5
|  |  | 596 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 640 | 0 | 640 | 33.75% | 12% | 347.2 | 43.4 | 40
|  |  | July | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
Totals |  |  | Capacity
Total Hours Before Time Off |  |  | 596
Max Possible Hours After Time Off |  |  | 640
Hours Available after Training, QA, Support, and Meetings |  |  | 347.2
Estimated Capacity (in approx. Story Points) |  |  | 43.4
Final Agreed Upon Team Capacity (in Story Points) |  |  | 40
Buffer/Adjustments
Total Sprint Capacity |  |  | 40
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Decrease percentage to account for time required for work on other teams.
Note on S6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Required HR Training, Professional Development Days, QA and Release, Support work.
Note on T6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-1s, Stand-up, Grooming, Sprint Review, Sprint Retro, Sprint Planning, Town Halls, etc.

## CP S55
Capacity Planning | Sprint 55
|  |  |  | OPTION 1: | [10 empty] | OPTION 2:
|  |  |  | Allocate hours; enter availability per day | [10 empty] | Override Availability
Name | Title | Estimated % of Time Dedicated to this Team | Estimated Dedicated Hours (Calculated) | M 01 | Tu 02 | W 03 | Th 04 | F 05 | M 06 | Tu 07 | W 08 | Th 09 | F 10 | Hours Available (Calculated by Day Availability) | Time Off (Override) | Max Possible Capacity (Calculated) | % Time for Training, QA, and Support | Estimated Hours Dedicated to Team Meetings | Available Hours (Calculated) | Estimation = hours/8 (Calculated) | Planned Story Points | Notes and Comments
PA 1 | Product Analyst | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 30% | 12% | 46.4 | 5.8 | 5
PA 2 | Product Analyst | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 80% | 12% | 6.4 | 0.8 | 2
SE 1 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 2 | Software Engineer | 80% | 64 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 3 | Software Engineer | 85% | 68 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 20% | 12% | 54.4 | 6.8 | 6
SE 4 | Software Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 6
QA 1 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 50% | 12% | 30.4 | 3.8 | 4
QA 2 | QA Engineer | 100% | 80 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 80 |  | 80 | 25% | 12% | 50.4 | 6.3 | 5
|  |  | 596 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 640 | 0 | 640 | 33.75% | 12% | 347.2 | 43.4 | 40
|  |  | July | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
Totals |  |  | Capacity
Total Hours Before Time Off |  |  | 596
Max Possible Hours After Time Off |  |  | 640
Hours Available after Training, QA, Support, and Meetings |  |  | 347.2
Estimated Capacity (in approx. Story Points) |  |  | 43.4
Final Agreed Upon Team Capacity (in Story Points) |  |  | 40
Buffer/Adjustments
Total Sprint Capacity |  |  | 40
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Decrease percentage to account for time required for work on other teams.
Note on S6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Required HR Training, Professional Development Days, QA and Release, Support work.
Note on T6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-1s, Stand-up, Grooming, Sprint Review, Sprint Retro, Sprint Planning, Town Halls, etc.

## 4. CP Summary
Program Increment Capacity Summary
In order to plan work for a team, first determine team capacity. See Instructions below.
Iteration | Duration | 3-Sprint Avg Velocity (SPs) | Planned Capacity (SPs) | Load (Final Planned Work) | Load (Unplanned) | Start Date | End Date
Sprint 50 | 2-Weeks | 37 | 43.4 | 40 | 3.4
Sprint 51 | 2-Weeks | 37 | 43.4 | 40 | 3.4
Sprint 52 | 2-Weeks | 37 | 43.4 | 40 | 3.4
Sprint 53 | 2-Weeks | 37 | 43.4 | 40 | 3.4
Sprint 54 | 2-Weeks | 37 | 43.4 | 40 | 3.4
Sprint 55 | 2-Weeks | 37 | 43.4 | 40 | 3.4
Name | Title | S50 Max | S50 Plan | S51 Max | S51 Plan | S52 Max | S52 Plan | S53 Max | S53 Plan | S54 Max | S54 Plan | S55 Max | S55 Plan | Total Max | Total Plan
PA 1 | Product Analyst | 5.8 | 5 | 5.8 | 5 | 5.8 | 5 | 5.8 | 5 | 5.8 | 5 | 5.8 | 5 | 34.8 | 30
PA 2 | Product Analyst | 0.8 | 2 | 0.8 | 2 | 0.8 | 2 | 0.8 | 2 | 0.8 | 2 | 0.8 | 2 | 4.8 | 12
SE 1 | Software Engineer | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 40.8 | 36
SE 2 | Software Engineer | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 40.8 | 36
SE 3 | Software Engineer | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 6.8 | 6 | 40.8 | 36
SE 4 | Software Engineer | 6.3 | 6 | 6.3 | 6 | 6.3 | 6 | 6.3 | 6 | 6.3 | 6 | 6.3 | 6 | 37.8 | 36
QA 1 | Software Engineer | 3.8 | 4 | 3.8 | 4 | 3.8 | 4 | 3.8 | 4 | 3.8 | 4 | 3.8 | 4 | 22.8 | 24
QA 2 | Software Engineer | 6.3 | 5 | 6.3 | 5 | 6.3 | 5 | 6.3 | 5 | 6.3 | 5 | 6.3 | 5 | 37.8 | 30
Total |  | 43.4 | 40 | 43.4 | 40 | 43.4 | 40 | 43.4 | 40 | 43.4 | 40 | 43.4 | 40 | 260.4 | 240
Velocity - Number representing team's historical velocity in points per sprint Capacity - Number per future sprint representing team's historical velocity adjusted for availability changes Load - Sum of the story points allocated to a sprint Note: All three are described using story points (SP) not hours

## 5. Sprint Planning
Sprint Planning
Stories identified need to be scheduled into sprints. Program Increments can have 5-6 Sprints in total, aligning with Quarter end. For Example, a July-Sept PI will have 6 Sprints if started on the week of July 4th, but it will have only 5 Sprints if started on the week of July 18th.
| 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6
Feature Color Key | Sprint Name | Sprint 50 |  | Sprint Name | Sprint 51 |  | Sprint Name | Sprint 52 |  | Sprint Name | Sprint 53 |  | Sprint Name | Sprint 54 |  | Sprint Name | Sprint 55
Feature | Start Date | 2023-01-09 |  | Start Date | 2023-01-16 |  | Start Date | 2023-01-30 |  | Start Date | 2023-02-13 |  | Start Date | 2023-02-27 |  | Start Date | 2023-03-13
Feature | End Date | 2023-01-13 |  | End Date | 2023-01-27 |  | End Date | 2023-02-10 |  | End Date | 2023-02-24 |  | End Date | 2023-03-10 |  | End Date | 2023-03-24
Feature | Capacity | #REF! |  | Capacity | #REF! |  | Capacity | #REF! |  | Capacity | #REF! |  | Capacity | #REF! |  | Capacity | 40
Feature | Planned | #N/A |  | Planned | #N/A |  | Planned | #N/A |  | Planned | #N/A |  | Planned | #N/A |  | Planned | #N/A
Feature | Vacations |  |  | Vacations |  |  | Vacations |  |  | Vacations |  |  | Vacations |  |  | Vacations
Feature
Feature
Feature
Feature
Feature
Feature
| Key | Summary | Points | Key | Summary | Points | Key | Summary | Points | Key | Summary | Points | Key | Summary | Points | Key | Summary | Points
Team |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
|  | #N/A | #N/A |  | #N/A | #N/A
[5 empty] | #N/A | #N/A
[5 empty] | #N/A | #N/A
[5 empty] | #N/A | #N/A
Infrastructure
Security
Architecture
Enablement
Note on B7: Use Format Painter to Copy Color to Feature Summary

## 6. Risks
Risks
Are there any risks to accomplishing the planned work?
1. Resolved – The risk is not a problem
2. Owned – A member of the team takes ownership of the item as it was not resolved in the meeting
3. Accepted – The risk cannot be resolved so it has to be understood and accepted for what it is
4. Mitigated – Formulate a plan to eradicate the risk.
After roaming exercise, risks that require further follow up during the PI are moved to the program risks board for further tracking.
Values
RISK Description | Likelihood | Impact | Severity | ROAM Status | Owner | JIRA Issue | Liklihood | Impact | Severity | ROAM Status
Example Risk | 1 | 3 | 3 | Owned | Team Member 1 | ITAPPS-12345 | 1 | 1 | 1 | Resolved
[7 empty] | 2 | 2 | 2 | Owned
[7 empty] | 3 | 3 | 3 | Accepted
[7 empty] | 4 | 4 | 4 | Mitigated
[7 empty] | 5 | 5 | 5

## 7. Confidence Vote
Confidence Vote |  |  |  |  | Average | High Confidence
How confident is each member of the team that we can accomplish all that has been planned? Place an X in only 1 of the columns for each team member.
Team Member Name | I don’t understand (0) | No Confidence (1) | Little Confidence (2) | Good Confidence (3) | High Confidence (4) | Very High Confidence (5) | Value | Vote
PA 1 |  |  |  |  | x |  | 0 | I don’t understand
PA 2 |  |  |  |  | x |  | 1 | No Confidence
SE 1 |  |  |  |  | x |  | 2 | Little Confidence
SE 2 |  |  |  |  | x |  | 3 | Good Confidence
SE 3 |  |  |  |  | x |  | 4 | High Confidence
SE 4 |  |  |  |  | x |  | 5 | Very High Confidence
QA 1 |  |  |  |  | x
QA 2 |  |  |  |  | x
Total Score | 0 | 0 | 0 | 0 | 32 | 0